# Growth-Evidence Corpus — Running Checklist

(paste into a new chat to resume; date: 2026-06-07)

## What this project is

Upgrade the Growth Tracker from a score tracker into a slide-level growth-evidence corpus: one row per student × lesson × slide holding the verbatim original answer, the feedback we sent, the revised answer, and rubric scores at each stage — queryable for research/reporting ("evidence improvement, don't just claim it").

## Decisions locked (2026-06-07)

- Grain: slide-level. ✓

- Feedback source: capture the pipeline-generated REWRITE.NOTES.<lesson> <name>.docx we already produce — no Gmail scraping. ✓

- Schoology text: reuse existing Workflow A / B1 extraction — no new Schoology API. ✓

- One long Evidence sheet, row-banded per student — not one tab per student (cross-student queries need a single filterable table). ✓

- Source of truth = Evidence sheet inside the Growth Tracker.

- Querying: today, Claude reads the Evidence sheet via Composio and answers research questions directly. FastMCP is the later scale-up.

## Evidence sheet schema (built, validated)

Class | Last | First | Email | Lesson | Slide # | Slide Type | Critical Aspect | Prompt | Original Answer | Feedback | Revised Answer | Conceptual/Depth/Writing-orig | Conceptual/Depth/Writing-rev | Rubric Source Tool: evidence_writer.py — deterministic; land_student_lesson(); re-runs update (no dupes); diagnostic slides only.

## Pilot status — Natural Selection (A_Day Biology)

Only lesson with a closed rewrite loop. 3 students landed with real verbatim data:

- Kenet Gutierrez Granados (NOTES 80 → DRAFT 100) — 7 slides

- Phenix Collins (60 → 92) — 8 slides

- Son'jai Thomas-Green (60 → 100) — 8 slides Originals ✓, prompts ✓, slide-keyed feedback ✓. Revised answers = PENDING (see blocker 1). (4th full-path student Victor Mendez Pablo 60 → 25 — add later as the instructive non-improver.)

## OPEN ITEMS / NEXT STEPS

- BLOCKER 1 — locate DRAFT (revised) docs. Student rewrite submissions do not surface by name search ("DRAFT NaturalSelection") yet DRAFT scores exist. Need to find where B1 read them from (likely a Schoology DRAFT assignment folder / course root). This is the missing half of the evidence.

- Refine feedback parse — guiding/push question bodies live in .docx table cells; current paragraph-only parse caught headers only. Make extraction table-aware. (Note: "Slide 13/22" text in the docx is identical across students = boilerplate/exemplar, NOT per-student revised work — ignore it.)

- Add B2 rubric sub-scores (Conceptual/Depth/Writing, orig + rev) into the Evidence rows — currently blank.

- Wire the Evidence-writer into the live pipeline: Workflow A lands originals, B1 lands revised, after each run (A already writes answers/<student>.json per run — just stop discarding it).

- Decide whether to write to the live Growth Tracker in Drive (download → openpyxl → LibreOffice recalc → re-upload) vs. keep a standalone corpus workbook.

- Backfill remaining in-scope lessons once DRAFT location is solved.

- FastMCP server (Phase 5, deferred) — local FastMCP over the corpus on the Mac, connected to Claude Desktop; tools like "feedback history around score X" and "all work on slide N across students." Needs: Python on Mac confirmed; corpus stable first.

- Define research queries: which slides drive most revision gain; which feedback moves drafts forward; student-type clustering.

- Upgrade Workflow C to emit evidence-backed growth narratives (quote slide-N original vs revised).

## Key IDs found this session

- A_Day NS NOTES folder: 1uUJX_ZUqZykQpR9F95fIP6fPZebI4cIz

- NS teacher template (Natural_Selection_VT): 1JWDRCr-kG29zkh5tn3xTadLkT1vO0ZjztqiouhaQh6Q (dup: 1NwU1sA6qCuNVlE8zx5VFON3aBFaiRY3_u8iJTmedyzg)

- NOTES decks: Kenet 1Vd7rC9ZryjopBC1L6e0bD0ERB0YcIn91CVX1S1x0szs · Phenix 1mZpca11TeVrvhzqECvSNLBh_rRdbTVC0z76aIT4yT18 · Son'jai 13S_o2RLNw5A3xVc55aVH7Y2FbG06KpcvG4TrcaNxNcE

- Feedback docx: Kenet 1bNyMC6mCaAlNifVndG15SpHiydHs59qe · Phenix 1hHR6WTYsNEhFOrdwWFU6rZODtwm58R-o · Son'jai 1nAwnL3oaQp5-RRKAMrXDPccvtWtFyjTU

- NS DRAFT folder: NOT FOUND (blocker 1)

## Note on the Lesson Index

The link in chat (…1JyH1DCRq…Z3Kn8) is the dead/404 index. Live index = 17wfpiu8bMXQkDnf78CtTCeDSycGpmAY_QPgCZKSeUOQ (Lesson Index (Do not move or delete)). No upload needed.